## Agile Sprint Backlog - delivera
AGILE SPRINT BACKLOG - Deliverable 1
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
US-01: Search Units (3 pts) | 3 | Komal/Parsa | To do | 4
Task 1.1: Backend Core Setup: Define Unit & User models in PostgreSQL and create authenticated API endpoints for fetching all unit data (ID, size, rate, status, etc.) (FR-01). | 1 | Parsa | To do | 1
Task 1.2: Frontend Display: Build the responsive React component to display the list of units retrieved from the API, ensuring a clear and organized view. | 1 | Komal | To do | 1
Task 1.3: Filtering Logic: Implement the advanced API search functionality to filter units by price range and availability status (FR-02), and integrate the filter controls into the React UI. | 1 | Komal/Parsa | To do | 1
Task 1.4: Project Structure QA: Write basic smoke tests for the unit API endpoint and ensure the Rails-React stack is stable and version-controlled on GitHub (NFR-05). | 1 | Midhat | To do | 1
US-02: Book Viewing (4 pts) | 5 | Midhat/Komal | To do | 4
Task 2.1: Appointment Model & API: Define the Appointment model, create the API endpoint for booking, and implement security controls for tenant access (NFR-02). | 2 | Parsa | To do | 1
Task 2.2: Conflict-Free Logic: Implement the critical backend validation that rejects new bookings if the selected time slot is already taken for that unit/clerk, enforcing (FR-03). | 1 | Komal | To do | 1
Task 2.3: Booking Form UI: Design and implement the React modal/page for tenants to select available units and specific time slots, providing immediate feedback on availability. | 1 | Midhat | To do | 1
Task 2.4: Clerk Viewing Dashboard: Build a simple Clerk interface (list view) to see all upcoming viewing appointments for their scheduled management. | 1 | Parsa/Midhat | To do | 1
US-03: Leasing Workflow (10 pts) | 10 | Parsa/Midhat | To do | 10
Task 3.1: Application Submission: Create the Application model and API endpoint (FR-04). Develop the comprehensive React application form with client-side validation for required fields (NFR-07). | 3 | Parsa/Midhat | To do | 3
Task 3.2: Clerk Approval Dashboard: Build the dedicated Clerk dashboard view to list all pending applications and link to the action interface (Approve/Reject). | 2 | Komal | To do | 2
Task 3.3: Lease Creation & Approval API: Implement the core business logic in the API to handle the Clerk's approval action (FR-05), which automatically creates a new Lease record in the database (FR-06). | 3 | Komal | To do | 3
Task 3.4: Validation & Transition: Ensure data safety and transactional consistency during the application approval and lease creation process (NFR-03). Write Minitest for the approval logic. | 2 | Parsa | To do | 2
US-04: Financial & Operations (9 pts) | 9 | Parsa/Komal | To do | 9
Task 4.1: Invoice Automation: Implement the Rails cron job/scheduler to automatically generate and save monthly invoice records for all active leases (FR-07). | 3 | Midhat | To do | 3
Task 4.2: Payment Recording: Implement the API logic for tenants/clerks to record payments and update the corresponding invoice status to "Paid" (FR-08). | 2 | Parsa | To do | 2
Task 4.3: Maintenance Ticket System: Create the Ticket model and API (FR-09). Build the Tenant UI form for submitting requests (priority, location). | 2 | Komal | To do | 2
Task 4.4: Operations Tracking: Build the basic Clerk dashboard to view, track, and update the status/priority of submitted maintenance tickets. | 2 | Parsa | To do | 2
User Story #5: Reporting & QA (9 pts) | 9 | Komal/Midhat | To do | 9
Task 5.1: Admin Reporting API: Create the backend API endpoints to aggregate data and calculate key metrics: occupancy rates, revenue, and open ticket counts (FR-10). | 3 | Komal | To do | 3
Task 5.2: Admin Dashboard UI: Build the protected Admin UI to consume the reporting APIs and display interactive charts and visualizations (NFR-06). | 2 | Midhat | To do | 2
Task 5.3: Unit & Integration Testing: Conduct full-system QA, focusing on transactional logic. Run all unit and integration tests (Minitest, Jest) and resolve critical bugs (NFR-01, NFR-03). | 3 | Midhat | To do | 3
Task 5.4: Documentation & Handover: Finalize all project documentation, update the report, and prepare for presentation/submission. | 2 | Parsa | To do | 2
TOTAL |  |  |  | 73 | 0 | 0 | 0 | 0 | 0 | 0
D